## defect report
defect id | Test case id | defect summary | reproduced step | Test data | defect types | defect severity | defect priority | expeted result | actual result | tester name | attachments | status
2 | 2 | check login button | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standard_user password:secret_sauce | functionlity | high | medium | To open the dashboard properly | as per expected result but not show proper dashboard datlis | patel uttam | https://drive.google.com/file/d/1ZAOn0ivSytsP9DRQVvQzOZ0ExnZeJTlA/view?usp=drive_link | open
3 | 3 | check login button with wrong value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:stydugd password:shhdhdhd | functionlity | high | medium | to display validation massage in proper | as per expected result but not to display properly | patel uttam | https://drive.google.com/file/d/1tUgJ-gChXtxOg_5bEgQ-MTDjlEQ3ZRox/view?usp=drive_link | open
4 | 4 | check login button with blank or null value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password: | functionlity | high | medium | To display validation massage in proper | as per expected result but passwordis in red only username massage is their | patel uttam | https://drive.google.com/file/d/1dPDaEVuA6LQbR80kX0JnvQdrb7h7va-_/view?usp=sharing | open
5 | 5 | check login button with username it's correct and password is worng | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standard_user password:fgfgfgf | functionlity | high | medium | To display validation massage in proper | as per expected result but why user name is in redif it is correct | patel uttam | https://drive.google.com/file/d/1lNMhS8GjHUAWdXJieRRX7s_ArWt12umi/view?usp=sharing | open
6 | 6 | check login button with username is not right and password is correct | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:dfgfdhd password:secrect_sauce | functionlity | high | medium | To display validation massage in proper | as per expected result but why password is in red if it is correct | patel uttam | https://drive.google.com/file/d/15x-0zOTsmr5UxmSfcE7HMa9u0Rduwdnc/view?usp=drive_link | open
7 | 7 | check login button with username is blank and password is correct | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password:secrect_sauce | functionlity | high | medium | To display validation massage in proper | as per expected result but why password is in red if it is correct | patel uttam | https://drive.google.com/file/d/1Lwen686grHJgtfeueVpmjZs138fvEd1-/view?usp=drive_link | open
8 | 8 | check login button with username is correct and password is blank | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standrd_user password: | functionlity | high | medium | To display validation massage in proper | as per expected result but why username is in red if it is correct | patel uttam | https://drive.google.com/file/d/1H4FwXVFC2OWk8liv2TC6pJFpP2HVw1NT/view?usp=drive_link | open
9 | 9 | check login button with white space in username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standrd user password: | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1l9O9zc_jB1TmKDDYnahQfDavkCRz72k-/view?usp=drive_link | open
10 | 10 | check login button with spicial charchatre in username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:@#$%&@@ password: | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1oRvWkbtiHx6AM7y0yS0gBlG_eKRfqXpE/view?usp=drive_link | open
11 | 11 | check login button with only alpha charchter in username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:gyygdhfh password: | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1o4xlv2Yi2IfLXyG9_HdCjkYcFqFudgZb/view?usp=drive_link | open
12 | 12 | check login button with only length of username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:gyygdhfhhfddddddfhhhhhhdjdjdjdjdjdjdjjdjdjdjdj password: | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1R9C6HhhQiM12K7nUxAg9QHlyTFkwbpxZ/view?usp=drive_link | open
13 | 13 | check login button with only digit of username | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name0910172324 password: | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1I-nPLyiYWgKefDsy70aVhxnJQvklwJqJ/view?usp=drive_link | open
14 | 14 | check login button with correct username and white space in password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name:standard_user password: | functionlity | high | medium | To display validation massage in proper | as per expated result but why user name is in red. | patel uttam | https://drive.google.com/file/d/1EbKm4ebfcuMuPfE3nQ28D1fv15Qgp9_C/view?usp=drive_link | open
15 | 15 | check login button with only white space of password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password: | functionlity | high | medium | To display validation massage in proper | as per expated result but why only user name is required.and not show proper validation massage in password. | patel uttam | https://drive.google.com/file/d/1ptju-XqcqJmy-GbRsjtJvyGfhKfeXsTK/view?usp=drive_link | open
16 | 16 | check login button with only spacial character of password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password:#$@#@!@##$$% | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1Kj3_rgQLgv6XDE1ITCk9B5EcM6-QAMYl/view?usp=drive_link | open
17 | 17 | check login button with only length of password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password:ydyddhjdjhdhdhdhdhdhdhd | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1kBK_jUXte5HJ9CxJ7-oXV3sH67waK7-y/view?usp=drive_link | open
18 | 18 | check login button with white space between alpha charcter of password | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button | user name: password:uttam patel | functionlity | high | medium | To display validation massage in proper | not show proper validation massage . | patel uttam | https://drive.google.com/file/d/1Uk9D8gaTSL0Qb1_6zwm8Onp7Xl9IlIrN/view?usp=drive_link | open
20 | 20 | check all item menu | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4) click side menu 5)click all item menu | NA | critacal functionlity | high | high | to open all item menu | it's is not open that page | patel uttam | https://drive.google.com/file/d/1YChrKYF9mBnTju295fW-PZbOk0ulr65Z/view?usp=drive_link | open
21 | 21 | check about menu | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4) click side menu 5)click all about menu | NA | functionlity | high | low | to open about page | it's is not open the about page and redirct to anthore page. | patel uttam | https://drive.google.com/file/d/17rVzcj2Y96IYFrgFX62Xaj6zjV-Pd8qZ/view?usp=drive_link | open
22 | 22 | check reset app state menu | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4) click side menu 5)click on reset app state | NA | critacal functionlity | high | high | to reset app state page | it's is not reset the page . | patel uttam | https://drive.google.com/file/d/1zd5TTL53-WW7T39AUokZnvtGTGQ9TNf9/view?usp=drive_link | open
38 | 38 | check continue button blank value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button 8)click on checkout button. 9)click on continue button | first name: last name: Zip: | functionlity | high | medium | to show validation Massage in proper | as per expted result but why only first name is required;. | patel uttam | https://drive.google.com/file/d/189OUbinp9ujiBuA-5m8UO5pgXekOHGkJ/view?usp=drive_link | open
39 | 39 | check continue button blank value of last name and zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: uttam last name: Zip: | functionlity | high | medium | to show validation Massage in proper | as per expted result but why first name is in red and only last name is required;. | patel uttam | https://drive.google.com/file/d/1ema6Gw4AKZyLl_uZpthfPl9f1cHmsp-u/view?usp=drive_link | open
40 | 40 | check continue button with blank value of first name and zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: patel Zip: | functionlity | high | medium | to show validation Massage in proper | as per expted result but why last name is in red and only first name is required;. | patel uttam | https://drive.google.com/file/d/1PPUuG_-rm7Exr7KmRMcTgXYs9B5lfCAN/view?usp=drive_link | open
41 | 41 | check continue button blank value of first name and last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip:99991709 | functionlity | high | medium | to show validation Massage in proper | as per expted result but why zip code is in red and only first name is required;. | patel uttam | https://drive.google.com/file/d/14W0rpiHQzHQlaMB3JDQjXlfCqRAZMvbg/view?usp=drive_link | open
42 | 42 | check continue button with digits in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name:9999 last name: Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1eegal6aEem_ilGfxkvkX-_hKKhP0PTvQ/view?usp=drive_link | open
43 | 43 | check continue button with digits in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name:8005 Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1TlXO2yCWwle7u9OH_Qf_DFe-y0zjQxVT/view?usp=drive_link | open
44 | 44 | check continue button with whitespace in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: ut tam last name: Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1A945p739ub1o9UN8UGnYc7kEALLJXZZr/view?usp=drive_link | open
| 45 | check continue button with whitespace in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: eerufdjdjkkr Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/12XiYsaV7Y_eAzs9T_mWPLgaPYjs5m8xr/view?usp=drive_link | open
46 | 46 | check continue button with spcial character in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: @#@#@# last name: Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1WIUDooChRoct-pzAI0-TcUe77Wg4BRgw/view?usp=drive_link | open
46 | 46 | check continue button with spcial character in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: @#@#@# Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1FPeT6saMpPSAtYoEcrvFQ8WSCfTcFDWJ/view?usp=drive_link | open
48 | 48 | check continue button with length in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: jddhfdhfgddgfdfddgd last name: Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1TYnKKN6fX5araLWwtHYtZux1iK9BL7Be/view?usp=drive_link | open
49 | 49 | check continue button with length in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: jddhfdhfgddgfdfddgd Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1RdbsNTFZr-W5Gs9hokof04ZAn6_mjtF_/view?usp=drive_link | open
50 | 50 | check continue button with alpha charter and spacial charcter in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name:ru@hgfhf last name: Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/18keLT31huIlys6CHe2X8Ra3Q5QGBlk0R/view?usp=drive_link | open
51 | 51 | check continue button with alpha charter and spacial charcter in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: ru@hgfhf Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1ltk1GKNSgAuT0ONFEh8rvNTShhMVI8cM/view?usp=drive_link | open
52 | 52 | check continue button with digit and alpha charcter in first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: gdvg5gd last name: Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1c2_fpsaTSgPGcpRdahtxU3hTUSks8Fzm/view?usp=drive_link | open
53 | 53 | check continue button with digit and alpha charcter in last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: gdvg5gd Zip: | functionlity | high | medium | to show validation Massage in proper | not show proper validation massage | patel uttam | https://drive.google.com/file/d/1h4rGQQBRpizazbrHC0svvxrsb6l7AN34/view?usp=drive_link | open
54 | 54 | check continue button with blank value is zip code name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name:uttam last name: patel Zip: | functionlity | high | medium | to show validation Massage in proper | as per expactd result but why first name and last name is in red | patel uttam | https://drive.google.com/file/d/1h4rGQQBRpizazbrHC0svvxrsb6l7AN34/view?usp=drive_link | open
55 | 55 | check continue button with blank value is first name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: patel Zip:17092324 | functionlity | high | medium | to show validation Massage in proper | as per expactd result but why zip code and last name is in red | patel uttam | https://drive.google.com/file/d/1uWnCup5Tj3q-YfM7mGb4K0BneCKLTiXc/view?usp=drive_link | open
56 | 56 | check continue button with blank value is last name | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: uttam last name: Zip:09178005 | functionlity | high | medium | to show validation Massage in proper | as per expactd result but why zip code and first name is in red | patel uttam | https://drive.google.com/file/d/1OdG90licycxYC8kYOyyH2uYmPiDfy9Ei/view?usp=drive_link | open
57 | 57 | check continue button with alpha charter in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip huhudjcahu | functionlity+L40F40:N41F40:Q41F41:U41 | high | medium | to show validation Massage in proper | not show proper validaion massage. | patel uttam | https://drive.google.com/file/d/1jYhC8OyXYdAB3jRbpVYAgEyztlKsD3Xy/view?usp=drive_link | open
58 | 58 | check continue button with spcial charter in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip : @#@$#$ | functionlity | high | medium | to show validation Massage in proper | not show proper validaion massage. | patel uttam | https://drive.google.com/file/d/12tWa9YvaonCFkzkaV7YaJeB38UvCHKys/view?usp=drive_link | open
59 | 59 | check continue button with white space betwwen digits in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip : 8005 | functionlity | high | medium | to show validation Massage in proper | not show proper validaion massage. | patel uttam | https://drive.google.com/file/d/12PrrZfx26zy2qYNew3laLYVEBu6WSKh2/view?usp=sharing | open
60 | 60 | check continue button with All wrong value | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: 1709 last name:0910 Zip :8005 | functionlity | high | low | to show validation Massage in proper | not show proper validaion massage and also redirct to overview page. | patel uttam | https://drive.google.com/file/d/1Vqs-Pr8nLWQCgOpc0LEoSWTC3lXt7yB8/view?usp=sharing | open
61 | 61 | check continue button with alpha charater in zip code | 1)https://www.saucedemo.com/ 2)press enter key 3) click on login button 4)click on add to cart 5)click on continue shopping 6)click on link of product 7)click on add to cart button 8)click on checkout button. 9)click on continue button | first name: last name: Zip : 8005 | functionlity | high | low | to show validation Massage in proper | not show proper validaion massage. | patel uttam | https://drive.google.com/file/d/13bCvrDMfzaKWx7S_fEvS8kmGuEi3it2X/view?usp=drive_link | open